## Sprint 1
Sprint 1
| September 18 - 25 |  | Build and Deploy a demo Flask application to heroku
Sprint | week | # | Task | Assignee | Status | Hours | Dependency | Status
1 | September 18 - 25 | 1 | Design the database models | Divya, Krishna | Finished | 1
1 | September 18 - 25 | 2 | Implement Database models in python classes | Krishna | Finished | 1 | 1 | Finished
1 | September 18 - 25 | 3 | Learn about Flask and check tutorials | Divya | Finished | 1
1 | September 18 - 25 | 4 | Set up a demo flask application on localhost | Divya | Finished | 0.5 | 3 | Finished
1 | September 18 - 25 | 5 | Design API following API Design Principles | Krishna | Finished | 0.5
1 | September 18 - 25 | 6 | Create APIs to handle basic requests and API routes in Flask | Divya | Finished | 0.5 | 5 | Finished
1 | September 18 - 25 | 7 | Set up a Heroku Account | Divya | Finished | 0.5
1 | September 18 - 25 | 8 | Deploy to Heroku | Krishna | Finished | 0.5 | 7,8 | Finished
1 | September 18 - 25 | 9 | Plan next Sprint | Divya, Krishna | Finished | 0.5 | 9 | Finished
[5 empty] | Total Hours: | 6
|  |  |  | TeamLead: | Krishna
|  |  |  | Scrum master: | Divya
Scrum Meetings:
Every Thusday and Monday from 11:00 AM to 11:20 AM

## Sprint 2
Sprint 2
| Sept 26 - oct 2 |  | Deploy Basic APIs with Postgres and Flask application to heroku
Sprint | week | # | Task | Assignee | Status | Hours | Dependency | Status
2 | Sept 26 - oct 2 | 1 | Create demo PostgreSQL functions to be called from Flask | Divya | Finished | 1 |  | Finished
2 | Sept 26 - oct 2 | 2 | Set up the project structure - divide the project into layers | Krishna | Finished | 1 |  | Finished
2 | Sept 26 - oct 2 | 3 | Configure one or more routes and handle them in separate modules | Divya | Finished | 0.5 |  | Finished
2 | Sept 26 - oct 2 | 4 | Create a Middleware layer that connects database layer to routes module | Divya | Finished | 1 | 2,3 | Finished
2 | Sept 26 - oct 2 | 5 | Connect GitHub repository to Heroku | Krishna | Finished | 0.5 |  | Finished
2 | Sept 26 - oct 2 | 6 | Configure CI/CD on Heroku for automatic deployments | Krishna | Finished | 1 | 5 | Finished
2 | Sept 26 - oct 2 | 7 | Create a development pipeline on Heroku for Hufflepuff repository | Krishna | Finished | 0.5 | 6 | Finished
2 | Sept 26 - oct 2 | 8 | Test Continuous deployment by pushing to master branch. | Divya | Finished | 1 | 7 | Finished
2 | Sept 26 - oct 2 | 9 | Plan next Sprint | Divya, Krishna | Finished | 0.5 | 8 | Finished
|  |  |  | TeamLead: | Krishna
|  |  |  | Scrum master: | Divya
Scrum Meetings:
Every Thusday and Monday from 11:00 AM to 11:20 AM

## Sprint 3
Sprint 3
| Oct 03 - Oct 9 |  | Implement Flask-restplus for swagger API design documentation
Sprint | week | # | Task | Assignee | Status | Hours | Dependency | Status
3 | Oct 03 - Oct 9 | 1 | Check Swagger API design documentation | Krishna | Finished | 1 |  | Finished
3 | Oct 03 - Oct 9 | 2 | Research for plug-ins for creating swagger API Documentation | Krishna | Finished | 0.5 | 1 | Finished
3 | Oct 03 - Oct 9 | 3 | Check and Install Flask Restplus library | Divya | Finished | 1 |  | Finished
3 | Oct 03 - Oct 9 | 4 | Implement annotations for existing APIs | Divya | Finished | 1 | 2,3 | Finished
3 | Oct 03 - Oct 9 | 5 | Change APIs and establish new routes using Flask-restplus | Divya | Finished | 0.5 |  | Finished
3 | Oct 03 - Oct 9 | 6 | Establish response types to all APIs | Divya | Finished | 0.5 |  | Finished
3 | Oct 03 - Oct 9 | 7 | Create Middleware methods as helper functions to API routes | Krishna | Finished | 1 |  | Finished
3 | Oct 03 - Oct 9 | 8 | Re-design Database models to support required API functionality | Krishna | Finished | 1.5 | 5,6,7 | Finished
3 | Oct 03 - Oct 9 | 9 | Plan next Sprint | Divya, Krishna | Finished | 0.5 | 8 | Finished
|  |  |  | TeamLead: | Krishna
|  |  |  | Scrum master: | Divya
Scrum Meetings:
Every Thusday and Monday from 11:00 AM to 11:20 AM

## Sprint 4
Sprint 4
| Oct 10 - Oct 16 |  | Follow API Design Guidelines
Sprint | week | # | Task | Assignee | Status | Hours | Dependency | Status
4 | Oct 10 - Oct 16 | 1 | Check API design principles and review them | Divya | Finished | 0.5 |  | Finished
4 | Oct 10 - Oct 16 | 2 | Re-design the API following Design Principles | Divya | Finished | 1 |  | Finished
4 | Oct 10 - Oct 16 | 3 | Establish response types and statuses for all the API routes | Krishna | Finished | 0.5 |  | Finished
4 | Oct 10 - Oct 16 | 4 | Test API design and response types for all the API routes | Krishna | Finished | 1.5 | 1,2,3 | Finished
4 | Oct 10 - Oct 16 | 5 | Plan next Sprint | Divya, Krishna | Finished | 0.5 | 4 | Finished
|  |  |  | TeamLead: | Krishna
|  |  |  | Scrum master: | Divya
Scrum Meetings:
Every Thusday and Monday from 11:00 AM to 11:20 AM

## Sprint 5
Sprint 5
| Oct 17 - Oct 23 |  | Implement Data persistance
Sprint | week | # | Task | Assignee | Status | Hours | Dependency | Status
5 | Oct 17 - Oct 23 | 1 | Check libraries for adding data persistance to Flask Application | Divya | Finished | 0.5 |  | Finished
5 | Oct 17 - Oct 23 | 2 | Research sqlalchemy and install flask-sqlalchemy | Divya | Finished | 1 |  | Finished
5 | Oct 17 - Oct 23 | 3 | setup connection to Heroku PostgreSQL server | Krishna | Finished | 0.5 |  | Finished
5 | Oct 17 - Oct 23 | 4 | setup and implement a demo application to use PostgreSQL server | Krishna | Finished | 1.5 | 1,2,3 | Finished
5 | Oct 17 - Oct 23 | 5 | Create database connection and session and incorporate to app | Krishna | Finished | 0.5 |  | Finished
5 | Oct 17 - Oct 23 | 6 | Implement CRUD applications on basic resources | Krishna | Finished | 1.5 | 5 | Finished
5 | Oct 17 - Oct 23 | 7 | Create and test tables in PostgreSQL server | Divya | Finished | 1 |  | Finished
5 | Oct 17 - Oct 23 | 8 | Test the resources and some routes and check data persistance | Divya | Finished | 1.5 | 6 | Finished
5 | Oct 17 - Oct 23 | 9 | Plan next Sprint | Divya, Krishna | Finished | 0.5 | 8 | Finished
|  |  |  | TeamLead: | Krishna
|  |  |  | Scrum master: | Divya
Scrum Meetings:
Every Thusday and Monday from 11:00 AM to 11:20 AM

## Sprint 6
Sprint 6
| Oct 24 - Oct 30 |  | Code Reviews
Sprint | week | # | Task | Assignee | Status | Hours | Dependency | Status
6 | Oct 24 - Oct 30 | 1 | Conduct code review | Divya | Finished | 0.5 |  | Finished
6 | Oct 24 - Oct 30 | 2 | Create new branches to implement new features | Divya | Finished | 0.5 |  | Finished
6 | Oct 24 - Oct 30 | 3 | Complete working on these features | Krishna | Finished | 1 |  | Finished
6 | Oct 24 - Oct 30 | 4 | create different pull requests for these features | Krishna | Finished | 0.5 | 1,2,3 | Finished
6 | Oct 24 - Oct 30 | 5 | review and merge the code to the master branch | Krishna | Finished | 0.5 | 4 | Finished
6 | Oct 24 - Oct 30 | 6 | Plan next Sprint | Divya, Krishna | Finished | 0.5 | 5 | Finished
|  |  |  | TeamLead: | Krishna
|  |  |  | Scrum master: | Divya
Scrum Meetings:
Every Thusday and Monday from 11:00 AM to 11:20 AM

## Sprint 7
Sprint 7
| Oct 31 - Nov 6 |  | Code Reviews
Sprint | week | # | Task | Assignee | Status | Hours | Dependency | Status
7 | Oct 31 - Nov 6 | 1 | Design User model | Divya | Finished | 1 |  | Finished
7 | Oct 31 - Nov 6 | 2 | Create new branches to implement new features for User | Divya | Finished | 2 |  | Finished
7 | Oct 31 - Nov 6 | 3 | Complete working on these features | Krishna | Finished | 1 |  | Finished
7 | Oct 31 - Nov 6 | 4 | create different pull requests for these features | Krishna | Finished | 0.5 | 1,2,3 | Finished
7 | Oct 31 - Nov 6 | 5 | review and merge the code to the master branch | Krishna | Finished | 0.5 | 4 | Finished
7 | Oct 31 - Nov 6 | 6 | Plan next Sprint | Divya, Krishna | Finished | 0.5 | 5 | Finished
|  |  |  | TeamLead: | Krishna
|  |  |  | Scrum master: | Divya
Scrum Meetings:
Every Thusday and Monday from 11:00 AM to 11:20 AM

## Sprint 8
Sprint 8
| Nov 7 - Nov 14 |  | Code Reviews
Sprint | week | # | Task | Assignee | Status | Hours | Dependency | Status
8 | Nov 7 - Nov 14 | 1 | Design Loan model | Divya | Finished | 1 |  | Finished
8 | Nov 7 - Nov 14 | 2 | Create new branches to implement new features for User | Krishna | Finished | 2 |  | Finished
8 | Nov 7 - Nov 14 | 3 | Complete working on these features | Divya | Finished | 1 |  | Finished
8 | Nov 7 - Nov 14 | 4 | create different pull requests for these features | Divya | Finished | 1 | 1,2,3 | Finished
8 | Nov 7 - Nov 14 | 5 | review and merge the code to the master branch | Divya | Finished | 0.5 | 4 | Finished
8 | Nov 7 - Nov 14 | 6 | Plan next Sprint | Divya, Krishna | Finished | 0.5 | 5 | Finished
|  |  |  | TeamLead: | Krishna
|  |  |  | Scrum master: | Divya
Scrum Meetings:
Every Thusday and Monday from 11:00 AM to 11:20 AM

## Sprint 9
| Nov 15 - Nov 22 |  | Code Reviews
Sprint | week | # | Task | Assignee | Status | Hours | Dependency | Status
9 | Nov 15 - Nov 22 | 1 | Design lists,notes model | Krishna | Finished | 1 |  | Finished
9 | Nov 15 - Nov 22 | 2 | Create new branches to implement new features for lists,notes | Divya | Finished | 1.5 |  | Finished
9 | Nov 15 - Nov 22 | 3 | Complete working on these features | Krishna | Finished | 1 |  | Finished
9 | Nov 15 - Nov 22 | 4 | create different pull requests for these features | Divya | Finished | 0.5 | 1,2,3 | Finished
9 | Nov 15 - Nov 22 | 5 | review and merge the code to the master branch | Divya | Finished | 1.5 | 4 | Finished
9 | Nov 15 - Nov 22 | 6 | Plan next Sprint | Divya, Krishna | Finished | 0.5 | 5 | Finished
|  |  |  | TeamLead: | Krishna
|  |  |  | Scrum master: | Divya
Scrum Meetings:
Every Thusday and Monday from 11:00 AM to 11:20 AM

## Sprint 10
Sprint 10
| Nov 23 - Nov 29 |  | Code Reviews
Sprint | week | # | Task | Assignee | Status | Hours | Dependency | Status
10 | Nov 23 - Nov 29 | 1 | Figure out Email | Divya | Finished | 1 |  | Finished
10 | Nov 23 - Nov 29 | 2 | Add admin to send emails | Divya | Finished | 1.5 |  | Finished
10 | Nov 23 - Nov 29 | 3 | Complete working on these features | Krishna | Finished | 1 |  | Finished
10 | Nov 23 - Nov 29 | 4 | create different pull requests for these features | Krishna | Finished | 0.5 | 1,2,3 | Finished
10 | Nov 23 - Nov 29 | 5 | review and merge the code to the master branch | Divya | Finished | 1.5 | 4 | Finished
10 | Nov 23 - Nov 29 | 6 | Plan next Sprint | Divya, Krishna | Finished | 0.5 | 5 | Inprogress
|  |  |  | TeamLead: | Krishna
|  |  |  | Scrum master: | Divya
Scrum Meetings:
Every Thusday and Monday from 11:00 AM to 11:20 AM

## Sprint 11
Sprint 11
| Nov 30 - Dec 6 |  | Code Reviews
Sprint | week | # | Task | Assignee | Status | Hours | Dependency | Status
11 | Nov 30 - Dec 6 | 1 | Check out react | Divya, Krishna | Finished | 1 |  | Finished
11 | Nov 30 - Dec 6 | 2 | Work on react hangman | Divya, Krishna | Finished | 1.5 |  | Finished
11 | Nov 30 - Dec 6 | 3 | Work on testing services | Divya, Krishna | Finished | 1 |  | Finished
11 | Nov 30 - Dec 6 | 4 | Make final presesntation | Divya, Krishna | Finished | 0.5 | 1,2,3 | Finished
11 | Nov 30 - Dec 6 | 5 | Prepare for final class | Divya, Krishna | Finished | 1.5 | 4 | Finished
11 | Nov 30 - Dec 6 | 6 | Review all the work till now | Divya, Krishna | Finished | 0.5 | 5 | Finished
|  |  |  | TeamLead: | Krishna
|  |  |  | Scrum master: | Divya
Scrum Meetings:
Every Thusday and Monday from 11:00 AM to 11:20 AM